## Test Case
Project Name: | Mahfil App
Created by: | Faysal Mahmud
TC Start Date: | 2024-01-06
TC End Date: | 2024-02-06
Test Case Id | Type of Testing | Module | Test Case Description | Test Data | Test Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status
TC-1 | User Authentication | SignUp | Verify that UI element for Registration displayed correctly | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in | There should be a SignUp button or Create Account link for better UI | Not found as per expectation | Click here |  | Failed
TC-2 |  | SignUp:: Continue with Google | Verify that a user can successfully register using their Google account | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Google", 5) Choose a Google account, 6) Verify that the user is redirected to the app’s main page | The user is registered and logged in successfully | As expected |  |  | Passed
TC-3 |  |  | Verify that canceling the Google login process does not register the user | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Google", 5) Cancel the login process | The user remains on the registration page, and no account is created | As expected |  |  | Passed
TC-4 |  |  | Verify that using an invalid Google account or pre-registered google account shows an appropriate error message | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Google", 5) Try to login with an invalid Google account | An error message is displayed, and the user is prompted to try again | As expected a message shows "Please try a different email address" |  |  | Passed
TC-5 |  | SignUp:: Continue with Email | Verify that a user can successfully register using an email address and OTP | Email: faysal….@gmail.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Check the email for the OTP, 8) Enter a valid name and phone number, 9) Click on the "Save" button | The user is registered and logged in successfully | As expected |  |  | Passed
TC-6 |  |  | Verify that entering an invalid email format shows an appropriate error message | Email: xyz.com, xyz@tt.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter an invalid email address | An error message is displayed indicating the email format is invalid | Not found as per expectation |  |  | Failed
TC-7 |  |  | Verify that trying to register with an already registered email shows an appropriate error message. | Email: faysal….@gmail.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter an email address that is already registered | An error message is displayed indicating the email is already in use | Not found as per expectation |  |  | Failed
TC-8 |  |  | Verify that a user can request to resend the OTP if it is not received |  | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Wait for a while without receiving the OTP, 8) Click on the "Resend OTP" button | A new OTP is sent to the email, and the user is able to receive it | As expected |  |  | Passed
TC-9 |  |  | Verify that entering an incorrect OTP shows an appropriate error message | valid OTP: 4286 Invalid OTP: 6824 | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Enter an incorrect OTP in the app | An error message is displayed indicating the OTP is incorrect | An error message is displayed, "OTP doesn’t matched" |  |  | Passed
TC-10 |  |  | Verify that an expired OTP shows an appropriate error message | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Wait for the OTP to expire, 8) Enter the expired OTP in the app | An error message is displayed indicating the OTP has expired | Successfully Signed in to the app |  |  | Failed
TC-11 |  |  | Verify that entering valid name and phone number details completes the registration | Name: Faysal Mahmud; Phone: 01799424097 | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Enter the received OTP in the app, 8) Enter a valid name and phone number, 9) Click on the "Save" button | The user is registered and logged in successfully | As expected |  |  | Passed
TC-12 |  |  | Verify that leaving the name or phone number fields empty shows appropriate error messages | Name: Phone: 01799424097; Name: Faysal Phone: | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter a valid email address, 6) Click on the "Send OTP" button, 7) Enter the received OTP in the app, 8) Leave the name or phone number field empty phone number, 9) Click on the "Save" button | An error message is displayed indicating that the name or phone number is required | Not found as per expectation |  |  | Failed
TC-13 |  |  | Verify that all mandatory fields (email, OTP, name, phone number) are validated | Name: Phone: 01799424097 | 1) Open the app, 2) Try to register without filling in the required fields | Appropriate error messages are displayed indicating the mandatory fields | Not found as per expectation |  |  | Failed
TC-14 |  |  | Name field can have at least 3 characters and maximum 50 characters | N/A
TC-15 |  | Sign Up:: Continue another way:: Log in with Mobile | Verify that a user can successfully register using a mobile number, OTP, name, and email | Phone: 01799424097 Name: Faysal Email: faysal@gmail.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Continue another way, 5) Enter a valid mobile number, 6) Click on the "Send OTP" button, 7) Check the email for the OTP, 8) Enter a valid name and email, 9) Click on the "Save" button | The user is registered and logged in successfully | As expected |  |  | Passed
TC-16 |  |  | Verify that entering an invalid mobile number shows an appropriate error message | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Continue another way, 5) Enter an invalid mobile number, 6) Click on the "Send OTP" button | An error message is displayed indicating the mobile number is invalid | Doesn't accept invalid phone number
TC-17 |  |  | Verify that entering an incorrect OTP shows an appropriate error message | valid OTP: 3258 Invalid OTP: 6824 | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another way", 5) Enter a valid phoe number, 6) Click on the "Send OTP" button, 7) Enter an incorrect OTP in the app | An error message is displayed indicating the OTP is incorrect | An error message is displayed, "OTP doesn’t matched" |  |  | Passed
TC-18 |  |  | Verify that an expired OTP shows an appropriate error message | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another way", 5) Enter a valid phone number, 6) Click on the "Send OTP" button, 7) Wait for the OTP to expire, 8) Enter the expired OTP in the app | An error message is displayed indicating the OTP has expired | Successfully Signed in to the app |  |  | Failed
TC-19 |  |  | Verify that entering valid name and email details completes the registration | Name: Faysal Email: faysal@gmail.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another way", 5) Enter a valid phone number, 6) Click on the "Send OTP" button, 7)Enter a valid name and email, 8) Click on the "Save" button | The user is registered and logged in successfully | As expected |  |  | Passed
TC-20 |  |  | Verify that leaving the name or email fields empty shows appropriate error messages | Name: Faysal Email: Name: Email:faysal@gmail.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another way", 5) Enter a valid phone number, 6) Click on the "Send OTP" button, 7)Leave the name or email field empty, 8) Click on the "Save" button | An error message is displayed indicating that the name or email is required | Not found as per expectation |  |  | Failed
TC-21 |  |  | Verify that entering an invalid email format shows an appropriate error message | Email: jlflajja@gg.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another way", 5) Enter a valid phone number, 6) Click on the "Send OTP" button, 7)Enter an invalid email format, 8) Click on the "Save" button | An error message is displayed indicating the email format is invalid | Successfully Signed in to the app |  |  | Failed
TC-22 |  |  | Verify that all mandatory fields (Phone, OTP, name, email) are validated | Phone: ; Phone: 01799424097 Name: email: faysal@gmail.com | 1) Open the app, 2) Try to register without filling in the required fields | Appropriate error messages are displayed indicating the mandatory fields | Not found as per expectation |  |  | Failed
TC-23 |  | Sign in:: Continue with Google | Verify that a user can successfully sign in using their Google account | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Google", 5) Choose the registered Google account | The user is signed in and redirected to the app’s main page | Successfully signed in but still in the navigation bar, not redirected to the home page |  |  | Passed
TC-24 |  |  | Verify that using an invalid Google account shows an appropriate error message | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Google", 5) Attempt to login with an invalid Google account | An error message is displayed, and the user remains on the sign-in page | As expected a message shows "Please try a different email address" |  |  | Passed
TC-25 |  | Sign in:: Continue with Email | Verify that a user can successfully sign in using their regestered email | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter the registered email address, 6) Get the OTP and submit, 7) Click on continue | The user is signed in and redirected to the app’s main page | Successfully signed in but still in the navigation bar, not redirected to the home page
TC-26 |  |  | Verify that entering an unregistered email shows an appropriate error message | Email: fjshffhas@gg.com | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter the unregistered email address | An error message is displayed indicating that the email is not registered | Not found as per expectation, rather it takes the invalid email as a new user |  |  | Failed
TC-27 |  | Sign in:: Continue another way:: Log in with Mobile | Verify that a user can successfully sign in using their mobile number and OTP | N/A | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another Way", 5) Enter the registered Phone number, 6) Get the OTP and submit, 7) Click on continue | The user is signed in and redirected to the app’s main page | Successfully signed in but still in the navigation bar, not redirected to the home page
TC-28 |  |  | Verify that entering an unregistered phone number shows an appropriate error message | Email: +8801555555555 | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue another Way", 5) Enter the unregistered phone number | An error message is displayed indicating that the email is not registered | Not found as per expectation, rather it takes the invalid phone number as a new user |  |  | Failed
TC-29 | Content Categories | Lecture Category Accessibility | Verify that the "Lecture" category is accessible from the footer and correctly displays relevant videos | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Lecture" category, 4) Verify that the page displays a list of lecture videos | The "Lecture" category page opens and displays a correctly organized list of lecture videos | As expected |  |  | Passed
TC-30 |  | Nasheed Category Accessibility | Verify that the "Nasheed" category is accessible from the footer and correctly displays relevant videos | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Nasheed" category, 4) Verify that the page displays a list of nasheed videos | The "Nasheed" category page opens and displays a correctly organized list of lecture videos | As expected |  |  | Passed
TC-31 |  | Telawat Category Accessibility | Verify that the "Telawat" category is accessible from the footer and correctly displays relevant videos | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Telawat" category, 4) Verify that the page displays a list of telawat videos | The "Telawat" category page opens and displays a correctly organized list of lecture videos | As expected |  |  | Passed
TC-32 | Video Streaming Functionality | Video Streaming for Lecture Content | Verify that lecture videos load quickly and play smoothly without buffering issues | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Lecture" category, 4)Select a lecture video to play, 5) Observe the video loading time and playback quality | The lecture video loads quickly and plays smoothly without buffering issues | As expected |  |  | Passed
TC-33 |  | Video Streaming for Nasheed Content | Verify that Nasheed videos load quickly and play smoothly without buffering issues | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Nasheed " category, 4)Select a Nasheed video to play, 5) Observe the video loading time and playback quality | The Nasheed video loads quickly and plays smoothly without buffering issues | As expected |  |  | Passed
TC-34 |  | Video Streaming for Telawat Content | Verify that Telawat videos load quickly and play smoothly without buffering issues | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Telawat " category, 4)Select a Telawat video to play, 5) Observe the video loading time and playback quality | The Telawat video loads quickly and plays smoothly without buffering issues | As expected |  |  | Passed
TC-35 |  | Video Streaming for Other Content | Verify that Other videos load quickly and play smoothly without buffering issues | N/A | 1) Open the app, 2) Navigate to the footer, 3) Click on the "Other" category, 4)Select a Telawat video to play, 5) Observe the video loading time and playback quality | The Other video loads quickly and plays smoothly without buffering issues | As expected |  |  | Passed
TC-36 |  | Video Playback Features:: Play and Pause | Verify that the video can be paused and played without issues | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video, 4) Pause the video, 5) Play the video again | The video pauses and resumes playing without issues | As expected |  |  | Passed
TC-37 |  | Video Playback Features:: Autoplay | Verify that the next video in the queue starts playing automatically after the current video ends, if autoplay is enabled | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video, 4) Ensure that autoplay is enabled, 5) Wait for the video to finish | The next video in the queue starts playing automatically after the current video ends | As expected |  |  | Passed
TC-38 |  | Video Playback Features:: Buffering | Verify that videos do not buffer excessively during playback | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video, 4) Ensure that autoplay is enabled, 5) Monitor the video for buffering during playback | The video plays smoothly without excessive buffering | As expected |  |  | Passed
TC-39 |  | Video Loading Time | Verify that videos load within an acceptable time frame | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video and measure the time taken for the video to start playing | The video starts playing within 2-3 seconds of selection | As expected |  |  | Passed
TC-40 |  | Video Quality Adjustment | Verify that the user can adjust the video quality | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video and Adjust the video quality settings (e.g., from 480p to 720p) | The video quality adjusts according to the selected setting without playback issues | As expected |  |  | Passed
TC-41 |  | Video Controls Visibility | Verify that video controls (play, pause, quality adjustment) are visible and functional | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video and Check the visibility and functionality of video controls | All video controls are visible and functional during playback | As expected |  |  | Passed
TC-42 |  | Full-Screen Playback | Verify that the video can be played in full-screen mode | N/A | 1) Open the app, 2) Select any video from any category, 3) Play the video and switch to full-screen mode | The video plays in full-screen mode without issues | As expected |  |  | Passed
TC-43 | Unique and Appropriate Video Content | Verify Unique Content | Verify that all videos on the app are unique and there are no duplicate videos | N/A | 1) Open the app, 2) Navigate to each video category, 3) Check for duplicate videos by comparing titles, descriptions, and content | All videos are unique with no duplicates in any category | As expected |  |  | Passed
TC-44 |  | Content Alignment with Islamic Principles | Verify that all content aligns with Islamic principles and teachings | N/A | 1) Open the app, 2) Navigate to each video category, 3) Randomly select and play videos, 4) Review the content for alignment with Islamic principles | All videos align with Islamic principles and teachings | As expected |  |  | Passed
TC-45 |  | Checking for Inappropriate Content | Verify that there is no inappropriate content in any video | N/A | 1) Open the app, 2) Navigate to each video category, 3) Randomly select and play videos, 4) Review the content for any inappropriate material | No inappropriate content is present in any video | As expected |  |  | Passed
TC-46 | Video Download Functionality | Download Video for Offline Viewing | Verify that users can download videos for offline viewing | N/A | 1) Open the app, 2) Navigate to a video, 3) Click on the download button, 4) Wait for the video to download | The video downloads successfully and is available for offline viewing | Not found as per expectation, rather the app prompts the user to upgrade to a premium account and does not allow the video to be downloaded |  |  | Failed
TC-47 | Search Functionality | Basic Search by Title | Verify that users can search for content using the video title | N/A | 1) Open the app, 2) Navigate to the search bar, 3) Enter the title of a known video, 4)Press the search button | The search results display videos matching the entered title | As expected |  |  | Passed
TC-48 |  | Search by Keyword | Verify that users can search for content using relevant keywords | N/A | 1) Open the app, 2) Navigate to the search bar, 3) Enter a keyword related to the content, 4)Press the search button | The search results display videos containing the entered keyword in their titles or descriptions | As expected |  |  | Passed
TC-49 |  | Search by Category | Verify that users can search for content by category | N/A | 1) Open the app, 2) Navigate to the search bar, 3) Select a category filter, 4)Press the search button | The search results are filtered to show only videos within the selected category that match the search term | As expected |  |  | Passed
TC-50 |  | Search with No Results | Verify the behavior when a search yields no results | N/A | 1) Open the app, 2) Navigate to the search bar, 3) Enter a random string or non-existent term, 4)Press the search button | The app displays a message indicating that no results were found for the entered search term | Not found as per expectation, rather shows random videos |  |  | Failed
TC-51 |  | Search Auto-Suggestions | Verify that the search bar provides auto-suggestions based on partial input | N/A | 1) Open the app, 2) Navigate to the search bar, 3) Enter the first few letters of a known video title or keyword | The search bar provides a list of auto-suggestions based on the entered partial input | Not found as per expectation |  |  | Failed
TC-52 | User Interaction | Like a Video | Verify that users can like a video and the like count is updated correctly | N/A | 1) Open the app and navigate to a video, 2) Click the "Like" button, 3) Observe the like count | The like button changes state (from white to filled), and the like count increases by one | As expected |  |  | Passed
TC-53 |  | Unlike a Video | Verify that users can unlike a video and the like count is updated correctly | N/A | 1) Open the app and navigate to a video, 2) Click the "Like" button again to unlike it, 3) Observe the like count | The like button reverts to its original state, and the like count decreases by one | As expected |  |  | Passed
TC-54 |  | Comment on a Video | Verify that users can add a comment to a video and it appears correctly | comment: wow | 1) Open the app and navigate to a video, 2) Go to the comments section, 3) Observe the comments section | The new comment appears at the top or bottom of the comments section, depending on the sorting order | As expected |  |  | Passed
TC-55 |  | Edit a Comment | Verify that users can edit their own comments and changes are saved correctly | Edited Comment: Masha Allah | 1) Open the app and navigate to a video, 2) Go to the comments section, 3) Find your comment and click the "Edit" button, 4) Modify the comment text and save it | The edited comment displays the updated text | As expected |  |  | Passed
TC-56 |  | Delete a Comment | Verify that users can delete their own comments | N/A | 1) Open the app and navigate to a video, 2) Go to the comments section, 3) Find your comment and click the "Delete" button | The comment is removed from the comments section | As expected |  |  | Passed
TC-57 |  | Share a Video | Verify that users can share a video via various platforms | N/A | 1) Open the app and navigate to a video, 2)Click the "Share" button, 3) Choose a sharing method, 4) Complete the sharing process | The video link is shared via the selected platform | As expected |  |  | Passed
Product Name |  | Walton Eplaza | TC Start Date | 2023-05-05 | TC Execution Start Date | 2023-05-07
Module Name |  | Register & Login | TC End Date | 2023-05-06 | TC Execution End Date | 2023-05-08
Epic |  |  | Test Case Developed By | Manik Hossain | Browser (tested) | Yes
Developer Name(TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes
Test Executed by

## Bug Report
Bug ID | Module | Bug Description | Environment | Steps to Execute | Expected Result | Actual Result | Bug Screen Shot
TC-1 | Sign up/ Create Account Button | The sign up/Create account button isn't easily visible | OS: Android 13, Device: Vivo Y22 | 1) Open the app 2) Click on the navbar icon on the top right corner 3) Scroll down and click on the Sign in button | There should be a SignUp button/ Create Account link for better UI | Not found as per expectation | Click here
TC-6 | SignUp:: Continue with Email | For entering an invalid email format there should be shown an appropriate error message |  | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter an invalid email address | An error message is displayed indicating the email format is invalid | Not found as per expectation | Click here
TC-7 | SignUp:: Continue with Email | Verify that trying to register with an already registered email shows an appropriate error message. |  | 1) Open the app, 2) Click on the navbar icon, 3) Scroll down and click on Sign in, 4) Select "Continue with Email", 5) Enter an email address that is already registered | An error message is displayed indicating the email is already in use | Not found as per expectation | Click here
TC-10 | SignUp:: Continue with Email | Verify that an expired OTP shows an appropriate error message |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue with Email" 5) Enter a valid email address 6) Click on the "Send OTP" button 7) Wait for the OTP to expire (120s), 8) Enter the expired OTP in the app | An error message is displayed indicating the OTP has expired | Not found as per expectation
TC-12 | SignUp:: Continue with Email | Verify that leaving the name or phone number fields empty shows appropriate error messages |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue with Email" 5) Enter a valid email address 6) Click on the "Send OTP" button 7) Enter the received OTP in the app, 8) Leave the name or phone number field empty phone number 9) Click on the "Save" button | An error message is displayed indicating that the name or phone number is required | Not found as per expectation | Click here
TC-13 | SignUp:: Continue with Email | Verify that all mandatory fields (email, OTP, name, phone number) are validated |  | 1) Open the app 2) Try to register without filling in the required fields | Appropriate error messages are displayed indicating the mandatory fields | Not found as per expectation | Click here
TC-18 | Sign Up:: Continue another way:: Log in with Mobile | Verify that an expired OTP shows an appropriate error message |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue another way" 5) Enter a valid phone number 6) Click on the "Send OTP" button 7) Wait for the OTP to expire 8) Enter the expired OTP in the app | An error message is displayed indicating the OTP has expired | Not found as per expectation
TC-20 | Sign Up:: Continue another way:: Log in with Mobile | Verify that leaving the name or email fields empty shows appropriate error messages |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue another way" 5) Enter a valid phone number 6) Click on the "Send OTP" button 7)Leave the name or email field empty 8) Click on the "Save" button | An error message is displayed indicating that the name or email is required | Not found as per expectation | Click here
TC-21 | Sign Up:: Continue another way:: Log in with Mobile | Verify that entering an invalid email format shows an appropriate error message |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue another way" 5) Enter a valid phone number 6) Click on the "Send OTP" button 7)Enter an invalid email format 8) Click on the "Save" button | An error message is displayed indicating the email format is invalid | Not found as per expectation
TC-22 | Sign Up:: Continue another way:: Log in with Mobile | Verify that all mandatory fields (Phone, OTP, name, email) are validated |  | 1) Open the app 2) Try to register without filling in the required fields | Appropriate error messages are displayed indicating the mandatory fields | Not found as per expectation | Click here
TC-26 | Sign in:: Continue with Email | Verify that entering an unregistered email shows an appropriate error message |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue with Email" 5) Enter the unregistered email address | An error message is displayed indicating that the email is not registered | Not found as per expectation, rather it takes the invalid email as a new user
TC-28 | Sign in:: Continue with Email | Verify that entering an unregistered phone number shows an appropriate error message |  | 1) Open the app 2) Click on the navbar icon 3) Scroll down and click on Sign in 4) Select "Continue another Way" 5) Enter the unregistered phone number | An error message is displayed indicating that the email is not registered | Not found as per expectation, rather it takes the invalid phone number as a new user
TC-46 | Download Video for Offline Viewing | Verify that users can download videos for offline viewing |  | 1) Open the app 2) Navigate to a video 3) Click on the download button 4) Wait for the video to download | The video downloads successfully and is available for offline viewing | Not found as per expectation, rather the app prompts the user to upgrade to a premium account and does not allow the video to be downloaded | Click here
TC-51